## Project Overview
PROJECT OVERVIEW | [56 empty] | Legend
|  |  | May | [15 empty] | June | [30 empty] | July | [7 empty] | Completed
|  | Week (#) | 3 | 16 | 17 | 18 | 19 | 20 | 21 | 4 | 23 | 24 | 25 | 26 | 27 | 28 | 5 | 30 | 31 | 32 | 33 | 34 | 35 | 6 | 37 | 38 | 39 | 40 | 41 | 42 | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [5 empty] | In Progress
|  | Day (Calendar) | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 |  |  | Planned
Sprint | Activity | Progress | [53 empty] | Notes |  | Dependency
1 – Development | Design/Development
Mockup | bar: 20 to 26
User Stories | bar: 20 to 26
Layout
Homepage | bar: 14; 16 to 31
Navbar | bar: 14; 16 to 17; 21 to 24; 26 to 30
Login | bar: 14 to 30
Sign Up | bar: 30; 14 to 30
Places | bar: 30; 14 to 19; 21 to 31
Users role | bar: 14 to 31
Reviews | bar: 15 to 19; 21 to 31
Sing up/Login
Sing up/Login with email | bar: 20
Facebook Oauth | bar: 20; 25 to 26
Users role | bar: 20 to 26
API
GeoCoder | bar: 27 to 31
Routhing | bar: 27 to 31
2 – Test | Cucumber
Sing up feature | bar: 29 to 2
Login feature | bar: 30 to 2
Edit account feature | bar: 30 to 2
Remove account feature | bar: 30 to 2
Edit place feature | bar: 31 to 2
Remove place feature | bar: 31 to 2
Edit review feature | bar: 31 to 2
Remove review feature | bar: 31 to 2
Rspec
Create user with invalid email
Create user without email
Create user without password
Create user with password and password_confirmation with different values
Create user with password shorter than 6 characters